July – September

- Determine type of event (e.g., seated dinner, reception)

- Meet with previous event committee to debrief and hand-off

- Build a budget (zero-based)

- Secure location to accommodate 200 guests comfortably based on type/format

- Finalize date around Enterprise Institute and global travel by KSWCS Committees

- Recruit a committee with two co-chairs and at least 12 more individuals.

  - Appoint sub-committee chairs for check-in and database, food & beverage, entertainment (includes a silent or live auction), program

  - 4-6 for check-in and check-out, including sub-committee chair

  - 1-2 for entertainment

  - 1 for food and beverage

  - 3 for auction support, if doing a live or silent auction

- Finalize ticket pricing

- Create sponsorship packages

October – December

- Begin soliciting members for their 2025-26 gift intentions for RI, ORE and Feed the Hungry.

  - Include fundraising event sponsorships if that is the direction needed.

  - Mail pledge forms for event sponsorships and send via email as soon as possible.

- Create a brand and theme for fundraiser and incorporate into sponsorship

  - Produce save-the-date material for website, email and snail mail

- Begin promoting in LiveOak and at lunches

- Committee meets monthly

- Register Best of Live ‘drawing’ with CA Attorney General

- Build out database with ticketing and sponsorship

January – March

- Finalize major sponsorship

- Begin soliciting auction items, if that will be part of the event

- Secure auctioneer, if a live auction is part of the event, three months out

- Reserve rentals (tables, chairs, linens, audio-visual)

- Secure photographer(s)

- Finalize menu

- Secure beverage donations

- Print Best of Live tickets, if doing live auction – five weeks out

- Finalize printed materials, including invitation, if using – four weeks out

- Promote Best of Live four weeks out

- Close out ticket sales three weeks out

- Mail, email and call sponsors to request guest names, email, phone five weeks out

- Call, email and mail ‘what to expect’ details to sponsors and guests one week out

April - June

- Send receipts and acknowledgment letters to all donors and ticket holders with FMV noted in text. (This is for tax deduction purposes.)

- Send out photo link to all guests

- Post images and relevant event facts in Live Oak, at luncheon after event and on social media channels

- Debrief on event

- Rest!