Minutes-Timeline:

Take The Lead 2015  (Thursday January 22, 2015, 7:45AM-3PM)

1/26/15  Unfortunately, I did not post follow up notes after 12/19/14.

12/19/14  Note:  It seems that the schools have so much going on that pressing them for commitment numbers prior to Thanksgiving is not very useful.  In retrospect at this time, my thought is that finding the speaker or speakers should be the first task, starting at least by Aug/Sep.  Then identify schools and their individual attendance goals.  Identify contacts at those schools, occasionally bugging them about signups.  In early December, send a flyer to each of the school principals, or through your school contact/Interact to remind them and give them a tool with which to sign up  students.  They should be given a stack of pre-printed sign-up forms, as well as having received a copy by email.  School contacts should be aware that the sign-up forms are mainly to make sure the students are aware that this is a commitment, and to give the school a list of participants.  We as the program administrators, do not need names or contact info of students.  We simply need a firm head count, in order to plan seating/scenarios/catering, etc.  We need this final count right after return from the holiday break.

12/17/14  Meet after club lunch w/ volunteers.  Update on program and roles.

12/11/14  Received Drama Scripts for Scenarios #2 and #6 from Catherine Kingsbury

11/19/14 Meet briefly w/ Roseanne Martin.  She and Rebecca will be lead for AHS

9-23-14  Meeting at Roost: Ken W; Dutch; Stan; Charles; Rich and Andrew Cherry.  Discussed having school person closest to student sign ups, as our main contact (provided by school admin).  Goal of 90 students and try for number commitment by Thanksgiving from each school.  Amended that day to 97:  AHS 35; Paso 10; Templeton 18; Del Rio 7; West Mall 4; Shandon 3; Morro Bay 10; Coast Union 10.  Rich will contact Ivan Bradley and Charles Herrera at AHS directly.  Coaches thought to be good source.  Andrew Cherry may have a lead on keynote speaker.

9-10-14  Email Gary Leffew-Email John Svinth at Shandon-Ask Charles to invite students.

9-3-14  Meeting: Ken W; Charles Bourbeau; Stan Cherry; Dutch; Rich J.  Ken lead us through steps to contact and enroll students at various schools.  Charles Bourbeau will be responsible for AHS; Del Rio-West Mall, and Shandon.  Stan will handle Paso; Templeton; MB; Coast Union. They received contact info.  Rich will make initial contact with Shandon and Grizzly Academy.  Other topics: Ask local President Elects to budget for participation; Consider community leaders such as Frank Meachum, Chief Haley, and/or school board members.  Rich will try to get RYLA exercise on “End of the World: who would you take w you”

8-29-12  Email Ross to see if he will do the food.

8-29-14  Paul, John H., and Rich met with EJ Rossi on several Rotary topics, including TTL.  Here are the TTL highlights:

1)  Mary Corey will be Interact, and we would like to have her do the Poker Hand and Love My Neighbor (assuming we keep those two exercises).  EJ will work at getting a TTL contact from the faculty, with a goal of having that person near the end of September.

2)  The school has some expanded technologies that make messaging to students much easier.  EJ encouraged us to send him teaser notes and/or videos, or links to videos, maybe brief parts of ethical scenarios, that he can now easily pass on to students.  In his words "to prime the pump".  He also suggested possibly a before and after survey, using the same messaging abilities.

3)  EJ will bring up TTL at the next faculty meeting to start the awareness.

4)  John H. suggested to EJ that Chris Bell (Not sure if I got the name right), the librarian and neighbor of John's, might be a good person as AHS contact for TTL.

5)  We re-confirmed the date as Thursday, January 22, 2015.

6)  EJ says the following are topics of current interest for scenarios:  Drinking; Pot; E cigs; Anonymity of social media; Bystander or Upstander?

7)  We discussed possible TTL speakers around the topic of diversity, which EJ thought could be good.

Paul, John, and Rich discussed a possible two speaker event where they either juxtaposed each other, or complement each other on the topic of diversity.

8-21-14 Email JP about rooms; Big John compiled evaluation comments (Music-less sitting-more group exchange-more activity-more breaks)

8-15-14  Meeting (Dutch, Paul, Big John, Rich)-Questions for EJ (How do we contact/remind/signup students? who will handle TTL? Can we involve kids on committee? PA school announcements?); Dutch will contact John Neil about sponsors; Budget estimate $35 per student; Give Cory til Sept 30 to confirm KSBY; Big John will review Evaluations for ideas; Idea: Video Conference Speaker; John confirmed Kiwanis will not be meeting on TTL

8-14-14  Dutch contacted Joan Brock.com about Keynote speaker

8-2-14 Pavilion Rental App sent

7-30-14  EM Jackie to develop AHS contacts

7-30-14  LM for Shanaya Fastje. Watched her video on bullying  818-736-5897

7-30-14 Stan Cherry and Charles Barbeau will laison with schools and with Rotary clubs

7-30-14 Email Gary Leffew at bullgurus@yahoo.com

7-28-14  Dutch confirmed Katherine Kingsbury would like to participate.

7-24-14  FB message to Gary Leffew, Bull Rider

7-23-14  Carol Bestkosny; Ron Mead will participate

7-23-14  Carl Dudley for MC?

7-22-14	Big John is Judge

7-22-14	Email Cory about KSBY; email Ken Weathers-School contact; Email Big John-judge

7-23-14  EJ says 1/22 is good.

7-22-14 Meet w Paul, Rich, and Dutch-Possible Judges: Big John; Grigger;

PossibleMCs:  (Contact KSBY Jeanette Trumpeter; Dave Hovde ??); Mitch Massey; Ken Johnston

Dutch will contact Katherine Kingsberry about doing drama scenarios

Rich-Big John (Judge)  Cory (KSBY)

Student Recruiters:  Ken Weathers; John Webster; John Donovan

Aim for 90 students – hope for 80 due to tables and trial  breakdown (10 tables)

Possible Speakers

7-14-14 Meet Paul-Dutch-Rich-Ken W

Possible club help:  Jessica; Carol; Cory; Big John; Diane R; Ron Mead; Ryan A; Rachelle

Carol B; Ross(food)

Sponsors-Ask John Neil to handle

Community leaders: Frank Meacham; School Board members; Rachelle

Jennifer Fanny-Kiwanis; Mary Corey??

Have lunch a little earlier (AHS lunch is 11ish)

Possible speakers: Gil Stork; Dave Hovde;

Verify date w EF Rossi-Rich