May 28, 2025

Rotary Fun Run Meeting

John, Layne, Linda, Anne

<https://runnercard.com/roadrace/public/raceGroup/977358>

* Packet pick up
	+ The racecourse is different
	+ 5K only
	+ Starting time is actually 7:15
	+ Packet pick up the night before or prior to the race at Bowman’s
		- Jordan will contact Bowman’s about registration location
		- Linda will help with this
* John and Layne met with Kaysville police
	+ Concerns with safety, crowd control, kids running out in street
* Crowd control
	+ Directing runners
		- John will finalize help from scouting troop
	+ Set up and take down
	+ Handing out water
	+ Food preparation (cutting up fruit)
		- We need to ask Bowman’s to donate fruit (oranges and banana’s) and water bottles – Anne will contact Becky to contact Bowmans
		- 700 water bottles
* Shirts
	+ Rotary logo
	+ Bowman’s logo
	+ Independence Day 5K Fun Run
* Volunteers
	+ Anne will create a chart on where the volunteers need to stand
	+ Two volunteers at each direction change
	+ Each volunteer will need to wear a yellow vest and flags
	+ Linda will order 20 vests and 20 flags
* Keith-can he bring his EZ-ups?