## Sheet1
CLUB SERVICE ACTION PLAN 2022-23
| Action/Tasks | Lead | Helper(s) | Resources Needed | Start | End | Metrics
Publicity & Image | Enhance Website Format | Leo | NA | ClubRunner | Begun | Ongoing | Member comments
| Establish PI Chair | President | Leo | Club Member |  | 2022-09-01 | PI Chair assigned
| Improve website & media content & reach | PI Chair | Leo | ClubRunner, Instagram, Facebook, Linkedin, Twitter (?) |  | Ongoing | Social media analytics
Meetings & Member Engagement | Improve Hybrid Meetings | Leo | Dennis? | Club Zoom account, camera(s), microphone(s), speaker(s), cables | 2022-08-01 | 2022-09-01 | Reduced setup time & glitches
| Provide Greeters at each meeting | Gerry | New members | Greeters, schedule | Begun | Ongoing | Greeter at each meeting
| Establish Rotary Minute | President | Leo, Dave, Gerry | Time during meetings | 2022-09-01 | Ongoing
| Hold field trip meetings, including Catalina State Park | President | Members | Dates, Locations | 2022-08-01 | Ongoing | Min 4 per RY
| Incorporate service projects in meetings | Service Chairs | President | Suitable projects, materials | 2022-09-01 | Ongoing | Min 4 per RY?
| Increase Club socials, including dinners at TOV rest\araunts | Charlene | ? | Dates, Locations | 2022-09-01 | 2023-06-30 | Min 4 socials per RY
Membership | Increase & diversify Club membership | Gerry | Dave? | Plan | Begun | Ongoing | Min 5% growth for RY
| Mentor new members | Gerry | Sr members | Mentors | 2022-08-01 | Ongoing | Mentor for each new member
| Establish new member orienttion program | Gerry | Dave? | Checklist, program | Begun | 2022-10-01 | Program established