Golf Tournament
Rotary Board Update
3/17/2025

I. Financials
a. Revenue Committed: 
i. Sponsorships:  $20,500 out of possible $23,500
· Still Need: Awards - $2,000; Skills: $1,000
ii. Tee and Green Sponsors
· 5 out of 30 available have been secured - $1,000.
iii. Teams:
· 1 Team registered, 4 have committed verbally; 6 given with sponsorships.
b. Expenses:
$1,000 due this week upon signing contract with golf course

II. Program Details:
a. May 5, 2025, Tennessee Grassland, Foxland Golf Course
b. Time Line:
i. 9:00 a.m. 	Volunteers will arrive.
ii. 9:30 a.m.  	Golfers Arrive
· Driving Range and Putting Green Open
iii. 10:00 a.m. 	Breakfast Served
iv. 11:00 a.m.	Shotgun Start
v. 5:00 p.m.	Tournament Ends / Ball Drop 
vi. 5:30 p.m.	Awards Ceremony / Cinco de Mayo Party
c. Teams to Accommodate: 32 total teams.
i. Teams needed 26 teams.
ii. 6 teams awarded to sponsors.
iii. 2 teams tee off per hole for par 4 and 5’s. Par 3 holes only 1 team
d. Food:  Brunch at 10:00 a.m. Bacon, eggs, chicken strips, etc
e. Ball Drop:  
i. Need to sell 1,500 golf balls. Priced as: 
· 1 for $20
· 3 for $55
· 6 for $110
· 9 for $165
· 11 for $200
ii. Purchasing used balls which will need to be hand numbered which will save thousands of dollars.
iii. Starts at 5:00 p.m.
· Tournament Ends / Ball Drop
f. Awards and Cinco de Mayo Party 
i. Starts at 5:30 
ii. Cinco de Mayo Party Ticket $25.00

III. Marketing / Publicity
a. Ball Drop: 
i. Asking each Rotarian to sell 20 tickets.
ii. Busy Bee will be marketing ball drop when they are on the radio & selling at the shop.
b. Team Recruitment
i. Contact last year’s teams.
ii. Push on social media posts. Boost if necessary.
c. Tee Sponsorships
i. Contact last year’s sponsors.
ii. Push on social media posts. Boost if necessary.
d. Event Overall
i. Get on the radio to promote.
ii. Create posters and flyers to be distributed















