Golf Tournament

Rotary Board Update

3/17/2025

- Financials

  - Revenue Committed:

    - Sponsorships:  $20,500 out of possible $23,500

      - Still Need: Awards - $2,000; Skills: $1,000

    - Tee and Green Sponsors

      - 5 out of 30 available have been secured - $1,000.

    - Teams:

      - 1 Team registered, 4 have committed verbally; 6 given with sponsorships.

  - Expenses:
$1,000 due this week upon signing contract with golf course

- Program Details:

  - May 5, 2025, Tennessee Grassland, Foxland Golf Course

  - Time Line:

    - 9:00 a.m. 	Volunteers will arrive.

    - 9:30 a.m.  	Golfers Arrive

      - Driving Range and Putting Green Open

    - 10:00 a.m. 	Breakfast Served

    - 11:00 a.m.	Shotgun Start

    - 5:00 p.m.	Tournament Ends / Ball Drop

    - 5:30 p.m.	Awards Ceremony / Cinco de Mayo Party

  - Teams to Accommodate: 32 total teams.

    - Teams needed 26 teams.

    - 6 teams awarded to sponsors.

    - 2 teams tee off per hole for par 4 and 5’s. Par 3 holes only 1 team

  - Food:  Brunch at 10:00 a.m. Bacon, eggs, chicken strips, etc

  - Ball Drop:

    - Need to sell 1,500 golf balls. Priced as:

      - 1 for $20

      - 3 for $55

      - 6 for $110

      - 9 for $165

      - 11 for $200

    - Purchasing used balls which will need to be hand numbered which will save thousands of dollars.

    - Starts at 5:00 p.m.

      - Tournament Ends / Ball Drop

  - Awards and Cinco de Mayo Party

    - Starts at 5:30

    - Cinco de Mayo Party Ticket $25.00

- Marketing / Publicity

  - Ball Drop:

    - Asking each Rotarian to sell 20 tickets.

    - Busy Bee will be marketing ball drop when they are on the radio & selling at the shop.

  - Team Recruitment

    - Contact last year’s teams.

    - Push on social media posts. Boost if necessary.

  - Tee Sponsorships

    - Contact last year’s sponsors.

    - Push on social media posts. Boost if necessary.

  - Event Overall

    - Get on the radio to promote.

    - Create posters and flyers to be distributed