PROJECT NAME: TopGolf Fundraiser

DATE OF PROJECT: 09/27/2022

# Overview:

Give a brief description of the project

This was a fundraising event for the RCSVCF at TopGolf.

# WHO:
Who worked on this project with you? What were their responsibilities? What were your responsibilities? Please provide contact information for all Rotarians involved.

Jon Lewis, Bob Baker, Rachel McKee, Lindsy Gardner, Jim Shepherd, Steve Gathings and Bo Porter. This was the committee who helped get people to sign up, donate items for the goody bag and stuff them, and handle registration at the event. My responsibilities were to enter into the contract with TopGolf, arrange for payment to TopGolf (half at contract signing and half right before the event…had to advance that on my credit card), coordinate signups with Bo, track signups and payments by those who signed up, publicize event, coordinate with Lindsy on updating the brochure and getting Bo to put same on DACdb, call and solicit swag for the goody bags, and solicit prizes for the winning team, worst team, best golfer and worst golfer.

# WHEN:
When did you/they start? Please provide as much detail as possible.

We started about 3 months before the event with publicizing the date. The contract was entered into about 2 months prior to the event.

# External Contacts:

Who did you coordinate with outside of Rotary? What role did they play? When do they need to be contacted for next year’s project? Please provide their contact information.

Ashley Moore of TopGolf (ashley.moore@topgolf.com direct # 205-847-2442). I would book the September 26, 2023 date at least 2 or 3 months ahead.

# Improvements Needed:

What could be done differently next year to make this project run more smoothly?

Maybe start calling members a month before the event to personally solicit signups.

Additional Information:

Please give any additional information you can think of that will help the next director to be successful. If anyone expressed a desire to help with this project in the future, please note that here.

I think most folks on the committee would help again plus can recruit additional committee members. The registrations and other TopGolf info including the brochure were under the calendar icon of our club on DACdb. There was a list of all the signups, and a place where you could sign up. It was under the 9-27-22 event on the calendar which was listed as the SVRC TopGolf event. On the financials, we had to pay half of the projected event cost at the signing of the contract. I got Bill Ross to make out a SVRCF check in July 2022 to TopGolf for $2,710.43 which was half the cost for 12 bays (up to 72 golfers). About a week before the event, it looked like we would only have 60 golfers/attendees, so we cut the contract to 10 bays/60 golfers. This resulted in a balance due of $2,124.37 which had to be paid 2 days before the event. Due to time constraints, I paid this with my AMEX card. I also paid a $300 cash tip to the TopGolf folks who served our group. Bill Ross reimbursed me with a SVRCF check of $2,424.37. So the total cost was $5,134.80, and the amount received/pledged as of the event was $12,700 leaving a balance of $7,565.20 raised for the SVRCF. Bo said several other donations have come in since the event, so I think the event raised right at $8,000 which was around $3,000 less than the 2021 event, but was still a good amount raised for the SVRCF. I don’t think we had a set goal, but we would have liked to have raised as much as in 2021 which was just under $11,000.

LOG INs / REPORTS:

If you had log-ins for systems/websites or accessed reports for this project, please include them below. Please include system/website, username, and password. For reports, please include which reports and how to access them.

All the signups and brochure material are in DACdb.