## Budget Total
Total Project Costs | Budget Quantity | Per Solution USD | Grand Total USD | GHS Total Cedis | Percent | Notes
School Books, Desks & Training (Solution 1) | See Detail | 7594.9212 | 7594.9212 | 43367 | 12.66%
Simple School (Solution 2) | 1 | 31412.8196 | 31412.8196 | 179367.2 | 52.38%
Microflush Toilets for Schools (Solution 3) | 30 | 500.8757 | 15551.6637 | 88800 | 25.93%
Computers and technology (Solution 4) |  | 2603.1524 | 2603.1524 | 14864 | 4.341%
Contingency |  |  | 2000 | 11420 | 3.335%
Signage |  |  | 300 | 1713 | 0.5003%
Monitoring by Sunyani Central Rotarians |  |  | 256 | 1461.76 | 0.4269%
Financial Fees |  |  | 250 | 1427.5 | 0.4169%
Grand Total for Yawhima Preschool Grant |  |  | 59968.5569 | 342420.46 | 100%
Financing amount |  |  | 59968.5
Difference in funding versus budget |  |  | -0.056918

## Budget Detail
Conversion Rate as of Dec 16, 2019 |  |  |  | Ghana Cedis (GHS) Exchange Rate $1 = | 5.71
Budget Item | Name of Supplier | Qty
Schools
School Books, Desks & Training (Solution 1) |  | 1 | Unit Cost Cedis | Unit Cost USD | Total Cedis | Total USD
Textbooks: Math, Science, English, Twi & French Languages, ICT and other books (Grades 1-6) | Ebenezer Bookshop | 1 | 4000 | 700.5254 | 4000 | 700.5254 | Note: See Books & Desks tab for details
Textbooks for Nursery & Kindergarten | Wise Furniture Co. Ltd | 1 | 7200 | 1260.9457 | 7200 | 1260.9457
Desks, Chairs and Tables | Wise Furniture Co. Ltd | 1 | 13750 | 2408.056 | 13750 | 2408.056
Library | Ebenezer Bookshop | 1 | 15417 | 2700 | 15417 | 2700
Training for Teachers | Sunyani Municipal District | 1 | 3000 | 525.394 | 3000 | 525.394
Total School Books, Desks & Training (Solution 1) |  |  | 43367 | 7594.9212 | 43367 | 7594.9212
School Blocks
Simple School (Solution 2) |  | 1 | Unit Cost Cedis | Unit Cost USD | Total Cedis | Total USD | Note: See School Construction tab for details
Substructure | Gyakum Company Ltd. |  | 10883 | 1905.9545 | 10883 | 1905.9545
Concrete Work | Gyakum Company Ltd. |  | 5349.2 | 936.8126 | 5349.2 | 936.8126
Block Work | Gyakum Company Ltd. |  | 1878 | 328.8967 | 1878 | 328.8967
Roofing and Carpentry | Gyakum Company Ltd. |  | 20108 | 3521.5412 | 20108 | 3521.5412
Joinery | Gyakum Company Ltd. |  | 24879 | 4357.0928 | 24879 | 4357.0928
Fittings and Fixtures | Gyakum Company Ltd. |  | 15371 | 2691.944 | 15371 | 2691.944
Floor, Wall & Ceiling Finishings | Gyakum Company Ltd. |  | 48870 | 8558.669 | 48870 | 8558.669
Painting & Decorating | Gyakum Company Ltd. |  | 13692 | 2397.8984 | 13692 | 2397.8984
External works and drainage | Gyakum Company Ltd. |  | 11837 | 2073.0298 | 11837 | 2073.0298
Labor | Gyakum Company Ltd. |  | 15000 | 2626.9702 | 15000 | 2626.9702
Project management @ 3% | Biyira Contracting Works |  | 11500 | 2014.0105 | 11500 | 2014.0105
Total Simple School (Solution 2) |  |  | 179367.2 | 31412.8196 | 179367.2 | 31412.8196
|  |  |  | (without labor & project mgt fee) | 152867.2 | 26771.8389
Qty
Microflush Toilets for Schools (Solution 3) |  | 30 | Unit Cost Cedis | Unit Cost USD | Total Cedis | Total USD
Plumbing & Building Supplies | Sucoff Ventures |  | 2000 | 350.2627 | 60000 | 10507.8809
Construction Labor | Sucoff Ventures |  | 860 | 150.613 | 25800 | 4518.3888
Sanitation, Health & Hygiene Training | Sucoff Ventures | 1 | 3000 | 525.394 | 3000 | 525.394
Total Microflush Toilets for Schools (Solution 3) |  |  | 2860 | 500.8757 | 88800 | 15551.6637
Computers and technology (Solution 4)
Computers | K. Fosu Enterprise |  | 7565 | 1324.8687 | 7565 | 1324.8687
TV Screen and Learning Materials | K. Fosu Enterprise |  | 7299 | 1278.2837 | 7299 | 1278.2837
Total Computers and technology (Solution 4) |  |  | 14864 | 2603.1524 | 14864 | 2603.1524
Contingency |  |  |  |  | 11420 | 2000 | Change on Budget Total Page
Signage | Peter Aboagye Antwi |  |  |  | 1713 | 300 | Change on Budget Total Page
Monitoring by Sunyani Central Rotarians | Goil Oil Station |  |  |  | 1461.76 | 256 | Change on Budget Total Page
Financial Fees | Fidelity Bank |  |  |  | 1427.5 | 250 | Change on Budget Total Page
Total Costs |  |  |  |  | 342420.46 | 59968.5569
* Items in BLUE are included in the online grants.rotary.org system

## School Construction Est.
Item | Description | Qty. | Unit | Rate | Amount GH¢ | USD $
Excavations And Earthwork
A | Excavate foundation trench not
| exceeding 1.5 meter deep commencing at | 10 | m3 | 3 | 30
150mm stripped level.
B | Excavate pit for column bases | 2 | m3 | 5 | 10
C | Extra over excavation and disposal in rocks | 4 | m3 | 8 | 32
D | Backfill around excavation with
| selected excavated materials. | 8 | m3 | 5 | 40
E | Load up and cart away surplus | 4 | m3 | 5 | 20
excavated materials from site.
Hardcore Filling
F | Imported hardcore filling placed and
| compacted in layers not exceeding 300mm | 45 | m3 | 12 | 540
to make up levels under floor.
CONCRETEWORK
Plain in-situ concrete (1:3:6-38mm
aggregate) as described:
G | Strip foundation 225mm thick | 3 | m3 | 160 | 480
H | Floor bed 125mm thick finished | 4 | m2 | 160 | 640
I | Blinding 100mm thick | 27 | m3 | 110 | 2970
| To Collection |  |  |  | 4762 | 833.9755
Item | Description | Rate | Unit | Qty. | Amount GH¢ | USD $
Reinforced in-situ concrete (1:2:4-19mm
aggregate) as described
A | Columns and Column Bases | 2 | m3 | 350 | 700
Mild Steel reinforcement to BS 785 as
described
B | 12mm diameter rod in columns | 171 | kg | 7 | 1197
C | 12mm diameter rod in column bases | 18 | kg | 7 | 126
D | 10mm diameter rod in stirrups | 36 | kg | 7 | 252
Formwork
Sawn Formwork to:
E | Vertical sides of column | 17 | m2 | 6 | 102
F | Edges of floor bed 125 high | 36 | m | 6 | 216
BLOCKWORK
Solid sandcrete blockwork bedded and
jointed in cement and sand (1:4) mortar
as described
G | 150mm Wall | 36 | m2 | 48 | 1728
Finishings
Cement and sand (1:4) mortar as
described:
H | 19mm Rendering to wall | 60 | m3 | 15 | 900
Painting and Decorating
Prepare and apply three (3) coats of
gloss oil paint to:
J | Wall | 60 | m3 | 15 | 900
| To Collection |  |  |  | 6121 | 1071.979
COLLECTION
| Page No. 1 |  |  |  | 4762 | 833.9755
| Page No. 2 |  |  |  | 6121 | 1071.979
SUBSTRUCTURE
| To Substructure Summary |  |  |  | 10883 | 1905.9545
Item | Description | Qty. | Unit | Rate | Amount GHC | USD $
SUPERSTRUCTURE
CONCRETEWORK
Reinforced in-situ concrete (1:2:4-19mm
aggregate) as described
A | Lintels/beam | 1 | m3 | 350 | 350
B | Columns | 3 | m3 | 350 | 1050
Reinforcement
Mild steel reinforcement to BS 785 as
described:
C | 12mm diameter rod in lintel/beam | 94 | kg | 7 | 658
D | 12mm diameter rod in column | 304 | kg | 7 | 2128
E | 10mm diameter rod as stirrups in lintel/beam | 18 | kg | 7 | 126
F | 10mm diameter rod as stirrups in column | 49 | kg | 7 | 343
Formwork
Sawn formwork to:
G | Vertical sides and soffit of lintel/beam | 17 | m3 | 12.6 | 214.2
H | Vertical side of column | 40 | m3 | 12 | 480
CONCRETEWORK
| To Concrete Summary |  |  |  | 5349.2 | 936.8126
BLOCKWORK
Sandcrete blockwork bedded and
jointed in cement and sand (1:4) mortar
as described:
J | 125mm Wall | 38 | m3 | 45 | 1710
K | 125mm precast decorative screen blocwork | 8 | m2 | 21 | 168
BLOCKWORK
| To Substructure Summary |  |  |  | 1878 | 328.8967
Item | Description | Qty. | Unit | Rate | Amount | USD $
ROOFING
A | 0.45 mm gauge corrugated aluminium
roofing sheets with two (2) corrugations side laps
& 150mm end laps fixed to hardwood supports with
| drive screws & washers strictly in accordance with | 176 | m3 | 58 | 10208
manufacturer's Instructions.
B | 600mm girth aluminium ridge caping ditto | 15 | m | 22 | 330
C | 600mm girth aluminium hip flashing ditto | 15 | m | 22 | 330
D | 600mm girth aluminium valley flashing ditto | 15 | m | 22 | 330
E | 300mm Wide 2-ply roof felt layer laid on blockwork
| wall filled between corrugated roofing sheet | 100 | m | 6 | 600
ROOFING
| To Summary |  |  |  | 11798 | 2066.1996
CARPENTRY
Sawn Treated hardwood as described
F | 50 x 100mm Sprokets | 100 | m | 10 | 1000
G | 50 x 100mm Purlins | 150 | m | 10 | 1500
H | 50 x 150mm Purlins | 250 | m | 15 | 3750
J | 50 x 150mm Hip rafters | 8 | m | 15 | 120
K | 50 x 150mm Valley rafters | 8 | m | 15 | 120
The following in 6No. Roof trusses approximately 7.3m
maximum span and 1.70m high hoisted 3.60m
above ground level
L | 50 x 150mm Rafters | 30 | m | 16 | 480
M | 50 x 150mm Strut | 40 | m | 16 | 640
N | 50 x 150mm Tie beam | 25 | m | 16 | 400
P | Allow the sum of GH¢100.00 for
| Carpenter's metalwork in respect of anchorage. |  |  |  | 150
Q | Allow the sum of GH¢200.00 for
| hoisting truss into position 3075mm above |  |  |  | 150
floor level.
R | Wall plate. timber member of the roof. | 75mmx100mm | m | Need to add | Need to add
sectional dimensions. Roof timber tie- beam
CARPENTRY
| To Summary | 20108 |  |  | 8310 | 1455.3415
Item | Description | Qty. | Unit | Rate | Amount | USD $
JOINERY
Wrot hardwood as described
Fascia/Verge Board
A | 25 x 300mm Fascia board | 82 | m | 16 | 1312
Doors And Windows
B | 15 x 500 x 44mm (finished) ledged framed
braced and battened window with 20 x 62.5mm stiles,
| braces, top and rails all nailed to 100 x 20mm tongued | 4 | No. | 120 | 480
and grooved hardwood boarding.
C | 525 x 1100mm ditto | 50 | No. | 75 | 3750
D | 675 x 1100mm ditto | 6 | No. | 75 | 450
E | 700 x 1100mm ditto | 1 | No. | 90 | 90
F | Extra over windows for rebated meeting styles | 45 | m | 10 | 450
Ledged, framed,braced and battened door comprising
G | 20 x 100mm vertical tongued and grooved boarding
| nailed to 20 x 150mm top and bottom ledges and | 2 | No. | 100 | 200
hanging styles and 20 x 150mm middle ledges and
braces with mortice and tenon joints at corners overall
size 650 x 2050 x 44mm thick.
H | Ditto size 700 x 2050 x 44mm thick. | 18 | No. | 200 | 3600
J | Ditto size 800 x 2050 x 44mm thick. | 5 | No. | 200 | 1000
K | Extra over windows for rebated meeting styles | 24 | m | 100 | 2400
Framed Frames
L | 50 x 150mm door and window frame plugged | 522 | m | 2 | 1044
to wall
M | 16mm diameter bar cut to length as burglar
| proofing in window frame for office and store | 45 | m | 12 | 540
Fillets, Glazing Beads and Grounds
N | 20 x 40mm Planted door stops | 288 | m | 10 | 2880
P | 20 x 40mm cover batten | 64 | m | 10 | 640
Q | 15 x 200 hardwood slats set on rake in window frame
| as fixed fan light. | 262 | m | 7 | 1834
| Total to collection |  |  |  | 20670 | 3619.965
Item | Description | Qty. | Unit | Rate | Amount GH¢ | USD $
JOINERY CONT.
Ironmongery
Provide and fix the following
ironmongery complete:
A | Pair T- hinges (medium) | 89 | No. | 5 | 445
B | Pair T- hinges (Large) | 31 | No. | 5 | 155
C | Italian security mortice lockset | 3 | No. | 120 | 360
D | 75mm Brass barrel bolt | 89 | No. | 6 | 534
E | 150mm Brass barrel bolt | 48 | No. | 6 | 288
F | Imported Hasp and Staple | 19 | No. | 10 | 190
G | Padlock (Approved Quality) | 16 | No. | 40 | 640
H | Set of 225mm brass window stays | 89 | No. | 8 | 712
J | Set of 225mm brass door stays | 29 | No. | 8 | 232
Burglar proofing
K | 50 x 50mm welded mesh size 1.20 x 1.00m | 2 | No. | 80 | 160
L | Ditto size 1.50 x 1.60m | 4 | No. | 80 | 320
M | Ditto size 2.25 x 1.60m | 1 | No. | 45 | 45
N | Extra over 50 x 50mm welded mesh for forming
| 150 x 150mm opening including framing sides with | 16 | No. | 8 | 128
20 x 40mm cover batten
| Total to collection |  |  |  | 4209
COLLECTION
| Page No. 5 |  |  |  | 20670
| Page No. 6 |  |  |  | 4209
JOINERY
| To Summary |  |  |  | 24879 | 4357.0928
Item | Description | Qty. | Unit | Rate | Amount GH¢ | USD $
FITTINGS AND FIXTURES
Wrought treated hardwood in:
Storage Shelves
A | 20mm thick horizontal and vertical boarding | 37 | m2 | 40 | 1480
B | 50 x 75mm plinth | 17 | m | 20 | 340
C | 50 x 50mm studs and runners | 62 | m | 20 | 1240
Reading top (Library)
D | 20mm thick exterior quality plywood 450mm wide lipped at | 13 | m | 65 | 845
edges with 20 x 12mm hardwood
E | 50 x 50mm braces, vertical or horizontal support | 18 | m | 20 | 360
Store shelving - Headteacher's office
F | 50 x 50mm vertical support, beare or horizonta runner | 67 | m | 30 | 2010
G | 50 x 50mm slats | 80 | m | 30 | 2400
Store shelving - Staff Common Room
H | 50 x 50mm vertical support, beare or horizonta runner | 62 | m | 30 | 1860
I | 50 x 50mm slats | 70 | m | 30 | 2100
Painting and Decorating
Knot, prime, stop and apply one undercoat and two
finishing coats of oil gloss paint on woodwork
J | Plywood or hardwood boarding | 45 | m2 | 24 | 1080
K | Picture rail not exceeding 100mm girth | 8 | m2 | 24 | 192
L | Frames etc not exceeding 300mm girth | 61 | m2 | 24 | 1464
FITTINGS AND FIXTURES
| To Summary |  |  |  | 15371 | 2691.944
Item | Description | Qty. | Unit | Rate | Amount GH¢ | USD $
PLASTERWORK AND OTHER
FLOOR, WALL AND CEILING
FINISHINGS
Cement and sand (1:4) mortar as
described
A | 13mm thick render to wall | 438 | m2 | 42 | 18396
B | 13mm thick render to wall and surfaces
| not exceeding 300mm | 21 | m2 | 42 | 882
C | 12mm render to isolated columns | 16 | m2 | 42 | 672
Bed and Backing
Cement and sand (1:3)
D | 38mm thick screeded bed laid on concrete | 185 | m2 | 25 | 4625
Chalkboard
E | 38mm thick Cement and sand (1:4) screeded backing | 13 | m2 | 25 | 325
Ceiling
Wrought treated hardwood
F | 12 x 38mm cover batten | 1020 | m | 8 | 8160
Plain sheet finishing
G | 1200 x 1200 x 3mm thick exterior quality plywood fixed to
| hard wood soffits(measured seperately) | 527 | m2 | 30 | 15810
PLASTERWORK AND OTHER
FLOOR, WALL AND CEILING
FINISHINGS
| To Summary |  |  |  | 48870 | 8558.669
Item | Description | Qty. | Unit | Rate | Amount GH¢ | USD $
PAINTING AND DECORATING
Prepare and apply three (3) coats of emulsion paint on:
A | Wall | 438 | m2 | 8 | 3504
B | Side of Columns | 21 | m2 | 8 | 168
C | Screen wall | 13 | m2 | 8 | 104
D | Plywood ceiling soffit | 527 | m2 | 8 | 4216
Prepare and apply one (1) undercoat and two (2)
finishing coats of oil paint as described on
E | Wall | 250 | m2 | 10 | 2500
F | Sides of column | 10 | m2 | 10 | 100
G | Welded mesh burglar proofing | 31 | m2 | 10 | 310
Prepare and apply one (1) undercoat and two (2)
finishing coats of oil paint as described on
H | General surfaces of door | 75 | m2 | 10 | 750
J | General surfaces of windows | 60 | m2 | 10 | 600
K | Door and window frames not exceeding 300mm girth | 81 | m2 | 10 | 810
L | Blackboard paint to chalk board | 13 | m2 | 10 | 130
M | Fascia or barge not exceeding 300mm girth | 20 | m2 | 10 | 200
N | Fixed fanlight over window/door including working paint into | 30 | m2 | 10 | 300
recesses and corners (measured flat overall)
PAINTING AND DECORATING
| To Painting and Decorating Summary |  |  |  | 13692 | 2397.8984
Item | Description | Qty. | Unit | Rate | Amount GHC | USD $
EXTERNAL WORKS AND DRAINAGE
Aprons and kerbed gravel beds
A | Excavate trench for kerb or dwarf wall not exceeding | 25 | m3 | 2 | 50
1.50m deep commencing at ground level
B | Remove excavated material from site | 16 | m3 | 5 | 80
C | Backfill around foundations with selected excavated | 9 | m3 | 5 | 45
material
D | Laterite filling to make up levels under aprons | 24 | m3 | 10 | 240
E | Concrete grade 15 in kerb footing or dwarf wall | 7 | m3 | 100 | 700
foundation
F | ditto in 75mm thick aprons | 40 | m2 | 40 | 1600
G | 100mm thick solid sandcrete blokwork in kerb laid | 70 | m | 25 | 1750
and jointed in cementmortar (1:3) 450mm high
H | 150mm thick gravel filling in bed | 50 | m2 | 30 | 1500
I | 100mm thick solid sandcrete blokwork in cement | 30 | m2 | 25 | 750
mortar (1:4) in dwarf wall
J | 25mm cement :sand (1:3) trowelled paving on apron | 79 | m2 | 25 | 1975
| Aprons & kerbed gravel beds: To Collection |  |  |  | 8690 | 1521.8914
Item | Description | Qty. | Unit | Rate | Amount GHC | USD $
Roof drainage and rainwater harvesting
A | 150mm diameter half round aluminium eaves
| gutter fixed to fascia with 6 x 125 x 450mm long | 78 | m | 6 | 468
galvanised steel brackets at 1 meter centers
B | Extra over last for outlet spigot | 2 | No. | 6 | 12
C | Extra over last for stopped end | 2 | No. | 6 | 12
D | 150mm diameter PVC pipe from outlet spigot | 6 | m | 20 | 120
to rainwater tank
E | 150mm diameter PVC bend | 4 | No. | 20 | 80
F | 'Polytank Rambo 450'' plastic water tank with
| 13mm brass tap mounted on blockwork | 1 | No. | 1000 | 1000
water tank supports (measured separately)
Roof drainage and rainwater harvesting:
| To Collection |  |  |  | 1692 | 296.3222
1No. Water tank supports
G | Excavate curved trench for tank stand not exceeding
| 1.50m deep commencing at ground level | 3 | m3 | 5 | 15
H | Remove excavated material from site | 2 | m3 | 5 | 10
J | Backfill around foundations with selected | 2 | m3 | 5 | 10
excavated materials
K | Sand filling to make up levels in tank stand | 2 | m3 | 40 | 80
L | Concrete grade 15 in foundation or tie beam | 2 | m3 | 300 | 600
M | Sawn formwork to sides of curved tie beam | 5 | m2 | 6 | 30
N | 50mm thick bed of fine sand in tank support | 4 | m2 | 35 | 140
P | 150mm solid sandcrete block in cement mortar (1:4) in | 12 | m2 | 30 | 360
curved wall
Q | 13mm thick cement and sand render (1:4) to side of curved | 7 | m2 | 30 | 210
wall
| 1No. Water tank supports: To Collection |  |  |  | 1455
Item | Description | Qty. | Unit | Rate | Amount GHC
COLLECTION
| Aprons and kerbed gravel beds |  |  |  | 8690
| Roof drainage and rainwater harvesting |  |  |  | 1692
| 1No. Water tank supports |  |  |  | 1455
EXTERNAL WORKS AND DRAINAGE
| To Summary |  |  |  | 11837 | 2073.0298
Item | Description | Qty. | Unit | Rate | Amount GHC | USD $
SUMMARY
A | SUBSTRUCTURE |  |  |  | 10883 | 1905.9545
B | CONCRETE WORK |  |  |  | 5349.2 | 936.8126
C | BLOCK WORK |  |  |  | 1878 | 328.8967
D | ROOFING |  |  |  | 11798 | 2066.1996 | 20108 | 3521.5412
E | CARPENTRY | 20108 |  |  | 8310 | 1455.3415
F | JOINERY |  |  |  | 24879 | 4357.0928
G | FITTINGS AND FIXTURES |  |  |  | 15371 | 2691.944
H | PLASTERWORK AND OTHER FLOOR, WALL AND CEILING FINISHINGS |  |  |  | 48870 | 8558.669
I | PAINTING AND DECORATING |  |  |  | 13692 | 2397.8984
J | EXTERNAL WORKS AND DRAINAGE |  |  |  | 11837 | 2073.0298
MAIN BLOCK
| To General Summary |  |  |  | 152867.2 | 26771.8389
| LABOR (3.9%) |  |  |  | 15000 | 2626.9702
| PROJECT MANAGEMENT (3%) |  |  |  | 11500 | 2014.0105
| GRAND TOTAL ESTIMATED COST OF WORKS |  |  |  | 179367.2 | 31412.8196

## Spend Plan
Spending Plan for Global Grant 19-82390
Yawhima Preschool 23 December 2019
Description of Project | Phase 1 USD | Phase 2 USD | Total USD
School Books, Desks & Training (Solution 1) | 0 | 7594.9212 | 7594.9212
Simple School (Solution 2) | 28069.8196 | 3343 | 31412.8196
Microflush Toilets for Schools (Solution 3) | 12000 | 3551.6637 | 15551.6637
Computers and technology (Solution 4) | 0 | 2603.1524 | 2603.1524
Contingency | 2500 | -500 | 2000
Signage | 0 | 300 | 300
Monitoring by Sunyani Central Rotarians | 200 | 56 | 256
Financial Fees | 200 | 50 | 250
Total Global Grant 19-82390 | 42969.8196 | 16998.7373 | 59968.5569

## Books & Desks Est.
Grades | Textbooks | Unit GHc | Qty | Total GHc | Total USD | 5.71 | Exchange Rate
1-6 | Math | 20 | 20 | 400 | 70.0525 | 3.3333 |  | 30
1-6 | English | 20 | 20 | 400 | 70.0525
1-6 | Creative Writing | 20 | 20 | 400 | 70.0525
1-6 | RME | 20 | 20 | 400 | 70.0525
1-6 | Science | 20 | 20 | 400 | 70.0525
1-6 | Twi | 20 | 20 | 400 | 70.0525
1-6 | French | 20 | 20 | 400 | 70.0525
1-6 | ICT | 20 | 20 | 400 | 70.0525
1-6 | Writing | 20 | 20 | 400 | 70.0525
4-6 | Citizenship | 20 | 20 | 400 | 70.0525
Total 1-6 |  |  |  | 4000 | 700.5254
Nursery | Nursery 1 & 2 | 20 | 35 | 700 | 122.5919
Nursery | Colouring Nursery | 20 | 35 | 700 | 122.5919
Kindergarten | Kindergarten | 20 | 35 | 700 | 122.5919
Total Nursery & Kindergarten |  |  |  | 2100 | 367.7758
Grand Total |  |  | 305 | 7200 | 1260.9457
Grades | Desks | Qty | Unit GHc | Total GHc | Total USD
PreK-KG | Dual Desks | 45 | 150 | 6750 | 1182.1366 |  | Used the lowest bid from Wise Furniture Co
PreK-KG | Teacher Tables | 8 | 200 | 1600 | 280.2102
PreK-KG | Teacher Chairs | 5 | 80 | 400 | 70.0525
Nursery & KG | Kindergarten Table | 10 | 350 | 3500 | 612.9597
Nursery & KG | Kindergarten Chairs | 60 | 25 | 1500 | 262.697
Total Desks, Chairs & Tables |  |  |  | 13750 | 2408.056
Technology
| 40" TV Monitor & mount |  | 1 | 2100 | 367.7758
| Laptop | 1000 | 2 | 2000 | 350.2627
| LED lighting |  |  | 2115 | 370.4028
| Locking cabinet |  | 1 | 3000 | 525.394
Total Technology for classrooms |  |  |  | 9215 | 1613.8354
Grand Total Textbooks, Furnishings, & Technology
|  |  |  | 30165 | 3669.0018
Funding for Library Books |  |  |  | 15417 | 2700
Grand total Books,Furnishings & Technology |  |  |  | 28660.5079 | 6369.0018

## City
Global Grant 19-90748 Communities: Simple Schools and Sanitation
Total beneficiaries are |  | 426 | estimated
Simple School (Solution 2)
School | Simple School Locations | Est People | District | Region | Option | Nearest City | Comments | Date & Time Visited
1 | Yawhima SDA Preschool | 120 | Sunyani Municipal |  |  | Sunyani | Build Preschool | Int. team site visit Sept 2019
| Grand Total | 120
Microflush Toilets for Schools (Solution 3)
| School Toilet Block Name | Est People | District | Region | Option | Nearest City | Comments | Date & Time Visited
11 | Yawhima SDA Preschool | 150 | Sunyani Municipal |  |  | Sunyani
11 | Yawhima SDA Elementary School | 300 | Sunyani Municipal |  |  | Sunyani
| Grand Total | 300 | (Preschool is already counted above)
School Desks & training (Solution 1)
| Task | Est People | District | Region | Option | Nearest City | Comments | Date & Time Visited
3 | Teacher to be trained for Yawhima SDA Preschool | 6 | Sunyani Municipal |  |  | Sunyani
| Grand Total | 6
| total | 126
Solar panals and Technology (Solution 4)
| School Name | Est People | District | Region | Option | Nearest City | Comments | Date & Time Visited
1 | Yawhima SDA Preschool | 90 | Sunyani Municipal |  |  | Sunyani | Soloar panel installation for tech
| Grand Total | 90 | (Already counted above)

## Estate School Costs
Item | Description | Qty | Unit | Rate | Amount (GH₵)
CONSTRUCTION OF 4-UNIT CLASSROOM BLOCK FOR YAWHIMA S.D.A
KINDARGARTEN
SUBSTRUCTURE (ALL PROVISIONAL)
Excavation and Earthworks
Site Preparation
A | Cut down trees not exceeding 600mm girth; grub
up roots, dispose offsite and fill void with laterite
| as directed | 3 | No | 120 | 360
B | Ditto; exceeding 600mm girth; do | 4 | No | 150 | 600
Excavation
C | Excavate trench for foundation not exceeding
| 1.50 meters deep commencing from ground level | 51 | M³ | 9.5 | 484.5
D | Excavate pit for column bases ditto | 11 | M³ | 15 | 165
E | Extra over excavation for excavating in rocks | 5 | M³ | 25 | 125
F | Backfill selected excavated material around
| foundation and compact | 33 | M³ | 5 | 165
G | Remove surplus excavated material from site
and deposite in spoil heaps not exceeding or
| spread and level | 29 | M³ | 7.5 | 217.5
Hardcore filling
H | Aproved imported laterite filled between walls in
layers not exceeding 300mm and watered and
| compacted to make up levels under floors | 335 | M³ | 15 | 5025
CONCRETE WORK
Plain concrete 1:4:8 38mm aggregate
J | Blinding 50mm thick | 11 | M³ | 12 | 132
Plain concrete (1:3:6:38mm agg) in:
K | Foundation | 12 | M³ | 500 | 6000
L | Floor slab125mm thick | 340 | M² | 62.5 | 21250
| To collection |  |  |  | 34524
2/1
Item | Description | Qty | Unit | Rate | Amount (GH₵)
Reinforced in-situ concrete (1:2:4-19 agg)as
descreibe in:
A | Column bases | 3 | M³ | 520 | 1560
B | Column | 1 | M³ | 520 | 520
REINFORCEMENT
Rolled Mild steel bar reinforcement to
B,S,4449 as described in:-
C | 10mm Diameter in column as strrrups | 78 | Kg | 3 | 234
D | 16mm Diameter in columns | 238 | Kg | 3.5 | 833
E | 16mm Diameter in columns bases | 389 | Kg | 3.5 | 1361.5
FORMWORK
Sawn Hardwood to:
F | Vetical sides of columns | 28 | M² | 7.5 | 210
G | Edge of concrete 125mm | 173 | M | 4 | 692
BLOCKWORK
Solid sandcrete blockwork in cement and sand
(1:4) mortar as described in:
H | 150mm Thick wals in foundation | 85 | M² | 65 | 5525
PLASTERWORK
12mm thick and sand (1:4) rendering as
described in:
J | Blockwall plinth | 36 | M² | 12 | 432
PAINTING AND DECORATING
Prepare and apply three coats of terracotta
paint on:
K | Rendered walls | 36 | M² | 8.5 | 306
| To collection |  |  |  | 11673.5
2/2
Item | Description | Qty | Unit | Rate | Amount (GH₵)
COLLECTION
| PAGE NO. 2/1 |  |  |  | 34524
| PAGE NO. 2/2 |  |  |  | 11673.5
SUBSTRUCTURE
| Carried To Summary |  |  |  | 46197.5
2/3
Item | Description | Qty | Unit | Rate | Amount (GH₵)
SUPERSTRUCTURE
CONCRETEWORK
Reinforce in-situ vibrated concrete (1:2:4-agg)
as described in:
A | Columns | 4 | M³ | 52 | 208
B | Beams | 9 | M³ | 52 | 468
REINFORCEMENT
Rolled mild steell bar reinforcement to 785 as
described in:
C | 10mm Diameter in beam, as ditto | 199 | Kg | 3 | 597
D | 10mm Diameter in beam, as ditto | 359 | Kg | 3 | 1077
E | 16mm Diameter in column | 497 | Kg | 3.5 | 1739.5
F | 16mm Diameter in beams | 777 | Kg | 3.5 | 2719.5
FORMWORK
Sawn Hardwood to:-
G | Vertical sides of columns | 70 | M² | 7.5 | 525
H | Sides of soffit of beams | 136 | M² | 7.5 | 1020
CONCRETWORK
| Carried To Summary |  |  |  | 8354
BLOCKWORK
Solid sandcrete blockwork in cement and sand
(1:4) mortar asdescribed in:
| 125mm Thick walls | 269 | M² | 58 | 15602
BLOCKWORK
| Carried To Summary |  |  |  | 15602
2/4
Item | Description | Qty | Unit | Rate | Amount (GH₵)
ROOFING
Corrugated or Trughed Sheet Roofing
A | 0.4mm corrugated aluzinc roofing sheets laid with
two corrugations side laps and 150mm end laps
| nailed to hardwood with drive screws and washer | 385 | M² | 25 | 9625
B | Ditto Ridge capping 450mm wide | 37 | M | 18 | 666
ROOFING
| Carried To Summary |  |  |  | 10291
CARPENTRY
Structural Timbers
Treated Sawned Hardwood
C | 50mm x 100mm purlins | 52 | M | 12 | 624
The Following in 5No. Roof Trusses 1014mm
span 1256mm rise with top and bottom chord
nailed together
D | 50mm x 100mm structs | 100 | M | 12 | 1200
E | 50mm x150mm Rafters | 52 | M | 12 | 624
F | 50mm x 150mm Tie Beam | 90 | M | 12 | 1080
0
G | Hoist roof truss and fix in position not exceeding |  |  |  | 0
| 2850mm high from room ground floor level | 5 | No | 250 | 1250
Carpenters Metalwork
H | 12mm Diameter 200mm long black bolt and
| washers fixing hardwood in truss members | 38 | No | 15 | 570
CARPENTRY
| Carried To Summary |  |  |  | 5348
2/5
Item | Description | Qty | Unit | Rate | Amount (GH₵)
JOINERY
WROUGHT HARDWOOD EAVES AND
BOARDING
A | 6mm Ordinary plywood fixed to bearers as caves
| and verge boarding | 47 | M² | 15 | 705
B | 25 x 250mm fascia and bording | 100 | M | 15 | 1500
Doors
400mm Thick (finished) panelled door
150mm wide stiles, top and middle rails and
200mmbottom rails and divided into four
panels and filled
C | Doors size 900x2550mm | 2 | No | 300 | 600
D | Door size 1200x2550mm | 4 | No | 350 | 1400
Window
300mm Thick (finished) panelled windows
150mm wide stiles, top and middle rails and
200mm bottom rails and divided into four
panels and filled
E | Size 1200x600mm | 2 | No | 220 | 440
F | Size 1200 x 1650mm | 18 | No | 250 | 4500
H | Extra for rebated stiles | 24 | No | 30 | 720
JOINERY
Wroughthardwood
Frames
J | 50 x 150mm frame plugged and screwed to
| blockwall | 153 | M | 15 | 2295
K | 50 x 150mm mullion and transume | 57 | M | 15 | 855
Fillers, stopes, Bcabs and Grounds
L | 12mm x 25mm plantedstop | 628 | M | 1.2 | 753.6
| To collection |  |  |  | 13768.6
2/6
Item | Description | Qty | Unit | Rate | Amount (GH₵)
IRONMOGERY
Supply and Fix the following Ironmongery to
hardwoodwith Screws to match
A | Pair 75mm brass butt hinges | 46 | No | 10 | 460
B | Pair 100mm ditto | 14 | No | 12 | 168
C | Brass barrel bolt 100mm long | 32 | No | 9 | 288
D | Elezttemortice lock with setof handel furniture | 4 | No | 100 | 400
| To Collection |  |  |  | 1316
COLLECTION
| PAGE NO. 2/6 |  |  |  | 13768.6
| PAGE NO. 2/7 |  |  |  | 1316
JOINERY
| Carried To Summary |  |  |  | 15084.6
2/7
Item | Description | Qty | Unit | Rate | Amount (GH₵)
METALWORK
Sundries
A | 50mm x 50mm galvanised iron welded mesh
burglar proofing cut to size and fixed to window
| opening (Office only¦) | 8 | M² | 15 | 120
METALWORK
| Carried To Summary |  |  |  | 120
PLASTERWORK AND OTHER FLOOR,
WALL AND CEILING FINISHES
In-situ Finishing
13mm thick cement and sand (1:4) rendering on:
B | Blockwall | 594 | M² | 12 | 7128
C | Isolated columns | 21 | M² | 15 | 315
D | Isolated beams | 47 | M² | 15 | 705
19mm thick cement and sand (1:4) mortar render
as described on:
E | Wall for Chalkboard | 25 | M² | 15 | 375
Cement and sand (1:4) mortar in:
F | 50mm sceeded bed laid level and trowelled hard
| and smooth on concrete floor | 339 | M² | 15 | 5085
Plain sheet finishing
G | 3mm thick ordinary plywood ceiling cards fixed
| to soffit of hardwood | 339 | M² | 15 | 5085
PLASTERWORK AND OTHER FLOOR,
WALL AND CEILING FINISHES
| Carried To Summary |  |  |  | 18693
ELECTRICAL INSTALLATION
Include the provisional sum of Twelve Thousand
| Ghana Cedis (GH₵ 12,000.00) electrical works |  | Item |  | 12000
ELECTRICAL INSTALLATION
| Carried To Summary |  |  |  | 12000
2/8
Item | Description | Qty | Unit | Rate | Amount (GH₵)
PAINTING AND DECORATION
Prepare and apply three coats of emulsion
paint on:
A | Rendered walls | 594 | M² | 12 | 7128
B | Isolated columns | 21 | M² | 12 | 252
C | Isolated beams | 47 | M² | 12 | 564
D | Soffit of plywood ceiling | 385 | M² | 15 | 5775
Prepare and prime back of joinery with
aluminium and wood primer before fixing
E | General surfaces of woodwork | 48 | M² | 15 | 720
Prepare and apply three coats of approved
renovator paint on:
F | Rendered Chalkboard | 25 | M² | 18 | 450
Prepare Knot, Prime, Stop and apply three
coats of hard gloss oil paint on:
G | Hardwood general surfaces | 52 | M² | 18 | 936
H | Ditto in narrow width not exceeding 300mm wide | 62 | M² | 18 | 1116
PAINTING AND DECORATION
| Carried To Summary |  |  |  | 16941
2/9
Item | Description | Qty | Unit | Rate | Amount (GH₵)
EXTERNAL WORKS
A | Excavate trench for apron wall not exceeding
| 1.50m deep commencing at ground level | 12 | M³ | 15 | 180
B | Remove excavated material from site | 4 | M³ | 5 | 20
C | Backfill around foundations with selected excavated
| materials | 9 | M³ | 7.5 | 67.5
D | Laterite filling to make up levels under aprons | 19 | M³ | 15 | 285
E | Concrete grade 15 in apron foundation | 4 | M³ | 57 | 228
F | Ditto in 100mm thick apron | 75 | M² | 57 | 4275
G | 100mm thick solid sandcrete blockwork in cement
| mortar (1:4) in dwarf wall | 56 | M² | 48 | 2688
H | 25mm cement :sand (1:3) trowelled paving on apron | 75 | M² | 20 | 1500
J | 13mm thick cement and sand render (1:4) to sides
| of apronwall | 75 | M² | 15 | 1125
K | Prepare and apply two coats of oil gloss paint on
| rendered wall | 56 | M² | 9 | 504
EXTERNAL WORKS
| Carried To Summary |  |  |  | 10872.5
Item | Description | Qty | Unit | Rate | Amount (GH₵)
SUMMARY
| SUBSTRUCTURE |  |  |  | 46197.5
| CONCRETWORK |  |  |  | 8354
| BLOCKWORK |  |  |  | 15602
| ROOFING |  |  |  | 10291
| CARPENTRY |  |  |  | 5348
| JOINERY |  |  |  | 15084.6
| METALWORK |  |  |  | 120
PLASTERWORK AND OTHER FLOOR,
| WALL AND CEILING FINISHES |  |  |  | 18693
| ELECTRICAL INSTALLATION |  |  |  | 12000
| PAINTING AND DECORATING |  |  |  | 16941
| EXTERNAL WORKS |  |  |  | 10872.5
| Carried to General Summary |  |  |  | 159503.6
Item | Description | Qty | Unit | Rate | Amount (GH₵)
GENERAL SUMMARY
| PRELIMINARIES |  |  |  | 7975.18
| 4 - UNIT CLASSROOM BLOCK |  |  |  | 159503.6
167478.78
| ADD CONTINGENCIES |  |  |  | 2015
| TOTAL ESTIMATED COST |  |  |  | 169493.78
9103

## Fund 82390
Yawhima Elementary School GG 19-82390 Rotary Clubs | Club # | Cash (US$) | 5% fee | DDF (US$) | Cash +5% | District | Status | Comment | Contact Name | Key Contact & Confirmed Funds? | Facebook
Sunyani Central, Ghana |  | 300 |  |  | 315 | 9102
Key Biscayne, FL |  | 6667 |  |  | 7000.35 | 6690
Rocky Mount, VA |  | 250 | 12.5 |  | 262.5 | 7570
Cheraw, SC |  | 4762 | 238.1 |  | 5000.1 | 7770
District 7770 |  |  |  | 5000 |  | 7770
District 6990 |  |  |  | 7000 |  | 6990
District 7690 |  |  |  | 4000 |  | 7690
District 7600 |  |  |  | 5000 |  | 7600
Subtotals, Cash & DDF |  | 11979 |  | 21000 | 12577.95
Total Funds Requested from TRF |  |  |  | 26989.5 |  |  |  |  | 14.5
Total Earmarked Rotary Funds |  |  |  | 59968.5
Additional Outside Funding |  |  |  | 0
Total Project Financing (must equal budget) |  |  |  | 59968.5
Total Budget |  |  |  | 59968.5569
Missing Funding |  |  |  | -0.056918

## Metrics
Column1 | Column2 | Column6 | Column7 | Area of Focus
Measure | Definition | Estimated | Solutions | Area of Focus
|  | Metrics: People | Impacted
Total number of direct beneficiaries | Individuals who receive clear and immediate benefit. | 426 | All Solutions Summarized Together | Clean Water,Sanitation and Hygiene; Basic Education and Literacy
People
Training of teachers in schools | Number of teachers trained | 6 | Solution #1 Training | Basic Education and Literacy
Number of students attending school for first time | How many students are attending school first time in their life. | 60 | Solution #2: Simple School | Basic Education and Literacy
People
Total children with new Microflush toilets | Number of children attending a Schools that has the use of a new bathroom for the first time. | 450 | Solutions #3: Microflush toilets | Clean Water,Sanitation and Hygiene
Students

## Actual Details 82390
Date | Solution | Supplier | Category | Detailed Description | Qty | UNIT PRICE (GHC) | AMOUNT (GHC) | Exchange Rate | Total USD | Contractor | Rec't | Bank Register?
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
[7 empty] | 0 | 5.22 | 0
0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.74 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 21.63
[7 empty] | 0 | 4.3 | 0
[7 empty] | 0 | 4.3 | 0

## Inc&Exp
| Global Grant 19-90743 Kumasi for Hiamankyene School |  |  |  | 4.5 |  | GHS to Dollar
INCOME & EXPENDITURE ACCOUNTS
2019-10-05
Date Paid | Income Description | Phase of Grant | Amount USD | Balance
|  | Phase 1 |  | 0
0
| Financial Fees |  |  | 0
0
| Financial Fees Wire Transfer |  |  | 0
| Total Income |  | 0
US Dollar Account: #####
Date | Vendor | Category | GHS | Deposit | USD Expenses |  | Ledger Balance | Purpose of Cheque
2019-10-05 | Opening Balance | [5 empty] | 0
| Financial Fees | Financial Fees |  |  |  |  | 0
| Deposit by Kumasi RC | [5 empty] | 0
| Deposit by The Rotary Foundation | [5 empty] | 0
| Wire Transfer Fee | Financial Fees |  |  |  |  | 0
| Transfer US Dollars to Ghana Cedis Acct | [5 empty] | 0
| Financial Fees | Financial Fees |  |  |  |  | 0
| Transfer US Dollars to Ghana Cedis Acct | [5 empty] | 0
|  |  |  | 0 | 0
GHS Account:#### |  |  |  | -49.512 | -49.512
Date Paid | Item Description | GHS Debit | GHS Credit | Balance | USD Expenses | Category | Actual Exchange Rate | Quoted Exchange Rate | GHS not Paid by Bank | On Bank Statement
2019-10-01 | Opening Balance |  |  |  |  | Deposit
| Financial Fees |  |  | 0 | #DIV/0! | Financial Fees
| Transfer from US Dollar to GHS Account |  |  | 0 | 0 |  | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0! |  |  |  | 0
|  |  |  | 0 | 0 |  |  | 5,5
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## Training
Title of Training | Objectives | Activities | Time Frame | Persons Involved | Expected Outcomes
Sanitation, hygiene, handwashing and microflush toilet use training | Train school children to use school Microflush toilet block | The host Rotarians will work with the students and teachers to learn how to use the new toilets | September 2020 to March 2021 | Seth Jiam of Sukoff Ventures and Host Rotarians will teach how to wash your hands and use new toilets. | The skills of hygiene, hand washing and use of microflush toilets will be gained.
Three-years of Ghana Govt Standard Teacher training | Teachers receive a BS in Education from University | The future teachers will receive a diploma certifying that they are qualified to teach at new preschool | 2016 to 2019 | University Professors will teach future teachers. | The teachers will get the skills to be certified to teach in Ghana.
One-year on-the-job training | Teachers are mentored for one year for practical teaching before being hired at new school. | The "student teachers" receive one-year of teaching under the supervision of a mentor teacher. | 2019-2020 | Mentor Teachers | The teachers receive one year of work experience under supervision of mentor teachers.
Numeracy, Literacy and Creative Art Training | Train Teachers by Sunyani Municipal District Assembly | The teachers will get supplemental Ghana teacher training that includes literacy, creative arts and numeracy. | 2021-08-01 | Host Rotarians and Mrs. Lydia Abrafi Nsiah, Education District training officer | The teachers gain additional skills valuable in their future teaching career.
Environmental Studies, Music and Physical Development | Train Teachers by Sunyani Municipal District Assembly | The teachers will get supplemental Ghana teacher training that includes environmental studies, music and physical education. | 2021-08-01 | Host Rotarians and Mrs. Lydia Abrafi Nsiah, Education District training officer | The teachers gain additional skills valuable in their future teaching career.
Creation of Learning Centers and Emergency Procedure Training | Train Teachers by Sunyani Municipal District Assembly | The teachers will get supplemental Ghana teacher training that includes how to set up learning centres and how to evacuate the classrooms in case of an emergency. | 2021-08-01 | Host Rotarians and Mrs. Lydia Abrafi Nsiah, Education District training officer | The teachers gain additional skills valuable in their future teaching career.
Supplemental Teacher training | Supplemental training provided by Rotarians who are university professors and administrators | The Rotarians will teach about empowering communities, developing leaders, setting goals, inspiring students and setting examples for students. | October 2021 to December 2021 | Host Rotarians and Mrs. Lydia Abrafi Nsiah, Education District training officer | The teachers will gain skills beyond the standard educational requirements. These outcomes stress the work Rotary does to transform communities.
Maintenance training for PTA and staff of school. | Training to reinforce maintenance, sustainability and stewardship of school and toilet blocks | The Rotarians will teach about maintenance and raising funds for needed maintenance. | October 2021 to December 2021 | Seth Jiam of Sukoff Ventures will teach about maintaining and using the Microflush toilet blocks. Rotarians will assist in this training. | The Parents and Teachers of the Yawhim PTA will learn the skills to properly maintain the school and the toilet blocks.

## Implementation Outline
Activity | Duration
Sunyani Central RC investigates Ways to fund simple school for Yawhima. Community needs assessments completed. | Jan 2019 to
2019-12-01
Develop and Submit grant proposal to TRF for a 3- room simple school with 3 ten Microflush toilet blocks | 2019-10-01
2019-12-01
Grant receives approval | 2020-04-01
Receive funds from TRF | 2020-06-01
Initiate and evaluate bids from appropriate contractors to build the simple school | 2020-02-01
2020-04-01
Award job to the suitable bidder and pay first payment to start the school | 2020-04-01
The construction of Yawhima preschool building | 2020-08-01
Construction of school furniture by wood workshop | 2020-10-01
2020-12-01
Build Microflush toilet at the school by Sucoff Ventures | 2020-09-01
2020-11-01
Sunyani Municipal District Education Directorate recruit, place and train teachers for the school | 2020-09-01
2021-01-01
WASH Training for teachers and attendants and community by Sucoff Ventures and Education Directorate School Health personnel | 2020-12-01
Commissioning of school and enrollment of new pupils for the school year 2020/2021 | 2021-02-01
Submit progress report on grant implementation | 2021-02-01
Collect first, second and third terms enrollment data for monitoring and reporting on grant matrix | 2021-02-01
2021-07-01
Submit final grant report | 2021-12-01

## TRF Payments
District | Club or District | Cash | Total | Received | Received | Key Contact
Total
Difference
DDF
World Fund