## Sheet1
Every case will be different based on the client and Community Resettlement Group - therefore this is a changing document
Activity | Timeline | Responsibility |  | Notes
These services should be provided with appropriate interpretation, if needed. |  | Affiliate | Community Resettlment Partner | We also want to ensure that our goals are: to help the client learn to probelm solve, only one person from the group will have contact with the case manager, the group will sign MOU to help the client for 4 months, the group takes a break.
Train co-sponsor and determine responsibilities of co-sponsor and affiliate | Pre-arrival | x
Background checks for all co-sponsors | Pre-arrival | x
Evidence of coordination with U.S. Tie | Pre-arrival | x
Evidence that agency prepared for arrival through pre-arrival services, coordination of housing, preparations for cases with significant medical conditions, or other special circumstances | Pre-arrival | X
Case File | Pre-arrival | x
Secure housing: temporary and/or permanent | Pre-arrival | x
Furnish Permanent Home with Tool Kit list, including culturally appropraite meal |  |  | x
Airport pickup (with appropriate interpretation, car seats for children and appropriate seasonal clothing) and transfer to housing | Arrival |  | x | USCRI would provide interpreter, as well as training, support and guidance from USCRI Staff
First Home Visit/Home Safety Orientation (next calendar day Visit/Home Safety form required) | 1 calendar day | x
Intake interview* (with appropriate interpretation) | 5 business days | x
Class A ( for physical disorders; mental health screening within 30 days for mental health disorders; notification to public health within 7 days) | appointment within 7 days | x
Class B (appropriate referral made in required timeframe, see Biodata) |  | x
Social Security Card | applied in 7 working days |  | x | This would be done with training, support and guidance from USCRI Staff
Medical Insurance (RMA, Medicaid) | applied in 7 working days | x
Medical Insurance Received | 10 days | x
Cash Assistance | applied in 7 working days | x
Cash Assistance Received/Denied | 10 days | x
Food Stamps | applied in 7 working days | x
Food Stamps Received/Denied |  | x
AR-11/Change of Address (assistance filling initial change of address) | submitted within 10 calendar days | x
Employment services | assistance with enrollment in 10 working days | x | x | Community Resettlement Partner would transport the client to the office to meet with the case manager
Non-employable services | assistance with enrollment in 10 working days |  | x | This would be done with training, support and guidance from USCRI Staff
ESL (assistance with enrollment in 10 working days) | assistance with enrollment in 10 working days |  | x | Community Resettelement Partner will work with client to enroll them and then conintue to encourage them to use English as much as possible .
Health Assessment: Referral date |  | x | x | USCRI staff would schedule the appointment and Community Resettlement Partner would Provide Transportation for the intial visits
Health Assessment: screening and immunizations | (w/in 30 days) | x | x | USCRI staff would schedule the appointment and Coummunity Resettlement Partner would Provide Transportation
Other Public Assistance (WIC; SSA; etc | applied in 30 working days |  | x | This would be done with training, support and guidance from USCRI Staff
Other Public Assistance Received/Denied |  |  | x | This would be done with training, support and guidance from USCRI Staff
Service Plan including family budget | completed within 30 days | x
Non-employable services | assistance with enrollment in 30 days |  | x | This would be done with training, support and guidance from USCRI Staff
School Enrollment | assistance with enrollment in 30 days |  | x | In corrdination with the School Impact USCRI Staff
Selective Service | (assistance with enrollment in 30 days) |  | x | This would be done with training, support and guidance from USCRI Staff
Pocket Money (within 30 days) | (within 30 days) | x
Adequate Food Allowance/Food Provision Provided (Until Food Stamps are available) |  |  | x | This would be done with the Food Pantry list that is provided for home set up and if the food stamps are delayed to assist with providing additional food until the food stamps begin
Second Home Visit | within 30 days; Second Home Visit form required | x
Cultural Orientation (completed for ALL case members 18 or older; Cultural Orientation provision form required) | within 30 days |  | x | This would be done with training, support and guidance from USCRI Staff
Cultural Orientation Assessment of Refugee Understanding | within 30 days |  | x | This would be done with training, support and guidance from USCRI Staff
R&P Period Report (*due on the 15th of the second month following 90th day) |  | x
Records of Public Welfare Notifications (confirm with dates from the above document column that the agency collected all appropriate notifications) |  | x
Household budget | completed within 90 days | x
Transportation - appointments, school enrollment, training to use the bus system | N/A |  | x | Community Resettlement Partner would train clients to use the public transist system
setting up bank account | N/A |  | x | This would be done with training, support and guidance from USCRI Staff
School Tutoring | N/A |  | x | In corrdination with the School Impact USCRI Staff
Job support | N/A |  | x | Community Resettlement Partner in coordination with case manager
Financial literacy | N/A |  | x | Community Resettlement Partner in coordination with case manager
Sign family up for Millbrook food pantry for first couple of months | on arrival |  | x | Community Resettlement Partner in coordination with case manager
teach them to pay bills on time |  |  | x | Community Resettlement Partner in coordination with case manager
teach them what to do with mail - what is important |  |  | x | Community Resettlement Partner in coordination with case manager
assist with issues in the home; light out, water etc |  |  | x | Community Resettlement Partner in coordination with case manager
Bus training |  |  | x | Community Resettlement Partner in coordination with case manager
Weekly Case note reports emailed to case manager |  |  | x | Community Resettlement Partner in coordination with case manager
Ensure that Co-sponors have fulfilled all their requirements |  | x